## Sheet1
Building Preservation | Cost | Time | Assumption
Continue to seek federal and state funding for building improvements and stabilization |  | 40 hours per month | part time role that peaks when grants are due and then drops off, but consistently looking for new opportunities
Create a vacant property registry to create a database of vacant properties and basic information (i.e. contact information of owner, reason for vacancy, building code compliance, upper story potential) |  | 40 hours to establish, 5 hours per week to maintain | staff person to develop in BSA (assessor?)
Adopt a property/building maintenance code that includes progressive fines for noncompliance; use fine to pay for enforcement | 5000 | 40 hours | modify the international property maintenance code; 40 x $125 (associate rate)
Consistently and equitably enforce the property maintenance code in a core designated area |  | 40 hours/week | full-time job - would this be done by the village?
Implement use of the existing GIS system for monitoring property status and conditions |  |  | Village just got BSA, the County has GIS, not sure it's realistic for the Village to get GIS soon
Using data from the vacant registry database and property maintenance code violations, develop criteria for which buildings downtown can be the focus for preservation; factors could also include significant historical events, cost of adaptive reuse, interest by community members | 20 hours |  | 2-3 meetings with stakeholders to develop criteria
Provide incentives to redevelop vacant properties based on findings | Depends on incentives | 50 hours | time to meet with village, main street, and stakeholder to develop a set of incentives
To actively recruit developers/investors to renovate existing unused buildings for mixed use development – Hang banners on historic buildings that explain its history and resources that can be used to rehabilitate the property to entice local investors. |  | 10 hours/building | LA to find cost of banner/plaque/sign, time for finding history of building, ordering banner, and hanging it
Provide grants/low interest loans for business owners to bring their buildings up to code and/or make necessary improvements |  |  | Someone who is administering loans should be full-time, qualified staff…
Create a vision for the priority properties for preservation with the community and market it broadly | $5,000 per property | 40 hours per property | set up the meetings, visiong for the property, find the data, format report, send it out, (cost=$40 x $125 associate fee)
Crowdsource funding from Calumet residents and visitors dedicated to historic preservation |  | 5 hours/week during the duration of the campaign | one person to set up the crowdfund and promote it
Publicly recognize individuals who improve their buildings or land through several channels |  | 5 hours/year | a notice in the paper or asmall ceremony
Recruit a team with historic restoration skills to teach destination workshops on craft techniques to both professionals and amateurs; harness where possible to perform actual improvements
Develop a program of cooperative building ownership where disparate small investors can fund a local team of restoration professionals to rehabilitate a building
| Cost | Time | Assumption
Outreach (Promotion)
Continue to seek federal and state funding for infrastructure and cultural resources |  | 40 hours/month | still want to flush out what this refers to
Identify volunteers and civic organizations that can adopt, maintain, and develop parks and green spaces and beautification projects |  | 10 hours/month | Someone to spend a couple hours a week finding volunteers through different organizations, and updating their contact information, coordinating volunteer activities
Collaborate with other area organizations to create a sustainable annual winter festival, featuring family outdoor activities, snow/ice sculpture, winter market, food, and music |  | 20 hours/week in lead up to event
Coordinate with Main Street Calumet's marketing and promotion activites |  | 2 hours/week
Work with KHNP to implement programs showcasing the Village's mining and union history, such as themed entertainment and live-action recreations
Business (Economic Vitality) | Cost | Time | Assumption
Hold regular meetings with business owners to discuss current and future planning |  | 5 hours/month
Develop a special assessment district to pay for snow removal |  |  | Role of Village Manager? Estimate of hours it would take Village Manager?
Connect business owners who are unsure of what to do with the business after they retire to agencies that can assist with a transition |  | 1 hour/month | Refer to Small Business Development Center; time is for person to keep in touch with business owners and connect themo to SBDC
Designate one day per week (or month) where businesses stay open later, i.e. the First Thursday of the month |  | 10 hours/month | someone to liaise with businesses, make any arrangements needed for downtown, promote
Partner with local/regional educational institutions to connect business owners to the workforce |  | 20 hours/quarter | reach out to educational institutions and business owners and try to connect them to fill the gaps in the workforce
Inventory downtown lodging opportunties and promote them in conjunction with events, including those outside the Village such as sports or outdoor recreation
Work to develop businesses that showcase the area's diverse ethnic history, suc h as themed restaurants
Design | Cost | Time | Assumption
Create a historic district overlay with design standards |  | 4-5 hours to discuss proposed standards? | This is in the ZO we created, that's essentially already done
Provide public realm amenities for patrons; benches, garbage and recycling bins |  |  | LAs to estimate
Study options for repurposing existing alleys in the Village |  |  | LAs to estimate - cost per lineal foot?
Create a local artist competition and display winning submissions downtown | 300 | 20 hours to coordinate event | for supplies for competitors or as prize money
Design the Sach’s and Calumet Theatre lot to be a public greenspace | 10000 | 20 hours/week for grantwriting | Taken from powerpoint "400 Block Community Garden Plan" in projects folder (and rounded up)
Work with local citizens interested in keeping vacant lots clean and maintained with an Adopt-a-Lot program |  | 10 hours/month | someone to do volunteer outreach and managing the Adopt-a lot program
Provide subtle interpretive markers relating to the NPS Downtown Calumet walking tour brochure
Work with the Village, NPS, and Calumet Township to create the wayfinding plan, coordination signage from key locations on Sixth Street, M-203/Pine Street, and U.S. 41/Calumet Avenue.
Encourage commercial businesses to develop street-related activities.
Improve and maintain Italian Hall Park and Red Jacket Road Park
Gateway treatments at both Sixth Street and Red Jacket Road
Directional and wayfinding program with a simple, consistent design that includes public parking and attractions
Access
Establish the Village's nonmotorized network, including connections to local and regional trails
Create a schedule of sidewalk, curb, and crosswalk improvements and maintenance to implement the network
Within the network, develop prioritized snow management procedures
Use Oak Street as a recreational, interpretive, and nonmotorized corridor
Consider interpreting the location of the historic streetcar route in Calumet
Conduct a sidewalk survey and develop a repair schedule that prioritizes links to the regional trail system |  | 20 hours | use volunteers to do a sidewalk audit downtown, create sheets for them to note conditions, work with DPW to prioritize